## Setup
plan_version_name | as_of_date | start_month | end_month
FY26 Q4 Synthetic Baseline | 2026-08-15 | 2026-09 | 2026-10

## Members
member_key | display_name | fte_type | status | current_hiref_id | hiref_end_date | role | level | effective_start | effective_end
member-synthetic-001 | Alex Example | STFTE | active | HIREF-SYNTH-ATLAS-001 | 2026-10-15 | Engineer | 7 | 2026-09-01
member-synthetic-002 | Blair Example | STFTE | active | HIREF-SYNTH-CEDAR-001 | 2026-10-31 | Engineer | 7 | 2026-09-01

## Projects
project_key | display_name | status | priority | start_date | target_end
project-synthetic-atlas | Project Atlas | active | 2 | 2026-09-01 | 2026-12-31
project-synthetic-beacon | Project Beacon | active | 3 | 2026-09-01 | 2026-12-31
project-synthetic-cedar | Project Cedar | active | 2 | 2026-09-01 | 2026-12-31

## Allocations
member_key | project_key | month | allocation
member-synthetic-001 | project-synthetic-beacon | 2026-09 | 0.5
member-synthetic-001 | project-synthetic-beacon | 2026-10 | 0.5
member-synthetic-002 | project-synthetic-cedar | 2026-09 | 0.8
member-synthetic-002 | project-synthetic-cedar | 2026-10 | 0.8

## Capacity
member_key | month | leave_fraction | bau_fraction | non_project_fraction
member-synthetic-001 | 2026-09 | 0 | 0 | 0
member-synthetic-001 | 2026-10 | 0 | 0 | 0
member-synthetic-002 | 2026-09 | 0 | 0 | 0
member-synthetic-002 | 2026-10 | 0 | 0 | 0

## HIREF Members
member_key | next_hiref_id
member-synthetic-002 | HIREF-SYNTH-CEDAR-NEXT

## HIREF Slots
hiref_id | project | request_type | start_date | end_date | notes
HIREF-SYNTH-ATLAS-001 | Project Atlas (project-synthetic-atlas) | extend | 2026-01-01 | 2026-10-15
HIREF-SYNTH-CEDAR-001 | Project Cedar (project-synthetic-cedar) | extend | 2026-03-01 | 2026-10-31
HIREF-SYNTH-CEDAR-NEXT | Project Cedar (project-synthetic-cedar) | extend | 2026-11-01 | 2027-06-30 | Renewal already identified
HIREF-SYNTH-OPEN-001 | Project Beacon (project-synthetic-beacon) | new | 2026-10-01 | 2027-03-31 | Open contractor demand SYNTHETIC_DATASET_V1

## HIREF Placeholders
placeholder_id | display_name | hiref_id | linked_member_key | resource_type | status | notes
placeholder-synthetic-001 | To Be Hired | HIREF-SYNTH-OPEN-001 |  | STFTE | planned | Open contractor demand

## HIREF Placeholder Allocations
placeholder_id | project_key | month | allocation
placeholder-synthetic-001 | project-synthetic-beacon | 2026-10 | 0.5